## Sheet2
Risk Register:
Risk ID | Risk Description | Probability | Impact | Risk Level | Mitigation Strategy | Owner | Status
R001 | Low participant registrations for events | Medium | Medium | Medium | Increase promotion through social media, posters, and student groups | Student Project Lead | Open
R002 | Volunteer shortage on event day | Medium | High | High | Maintain a backup volunteer list and assign standby volunteers | Volunteer Coordinator | Open
R003 | Internet or network failure during registration | High | High | High | Keep offline registration sheets and backup internet connection | Technical Team | Open
R004 | Incorrect registration data entered by participants | Medium | Medium | Medium | Validate form fields and review registrations before event day | Registration Team | Open
R005 | Venue becomes unavailable or changes at the last minute | Low | High | Medium | Identify an alternative venue in advance | Faculty Coordinator | Open
R006 | Delays in event schedule due to speaker or organizer issues | Medium | Medium | Medium | Maintain buffer time between sessions and communicate updates quickly | Event Coordinator | Open
R007 | Technical equipment failure (projector, microphone, laptop) | Medium | High | High | Test equipment before the event and keep backup devices available | Technical Team | Open
R008 | Dashboard displays incorrect metrics due to data errors | Medium | Medium | Medium | Perform data validation and testing before reporting | Student Project Lead | Open
R009 | Loss of collected data due to accidental deletion | Low | High | Medium | Schedule regular backups of Sheets, Excel files, and database | Student Project Lead | Open
R010 | Delayed report generation affecting event review | Medium | Low | Low | Automate reporting process using Python scripts | Student Project Lead | Open
Probability:
Rating | Description
Low | Unlikely to occur
Medium | May occur during the project
High | Likely to occur
Impact:
Rating | Description
Low | Minor effect on project activities
Medium | Noticeable disruption requiring attention
High | Significant impact on event operations