## Sheet1
StakeHolders Register:
StakeHolders | Role in Event | Interest in Project | Influence in Project | Communication method | Frequency of Communication
Faculty Coordinator | Oversees overall event activities and approvals | High | High | In person meetings, WhatsApp | Weekly
Student Project Lead | Responsible for project planning and execution | High | High | Daily tracking and meetings | Daily
Event Coordinators | Manage individual event activities | High | Medium | WhatsApp, Meetings | Weekly
Volunteers | Support registration, venue management, and event operations | Medium | Medium | WhatsApp Groups | Daily during event week
Participants | Register and attend events | Medium | Low | Email, Event Posters | As needed
Technical Team | Supports internet, systems, and technical setup | Medium | Medium | WhatsApp, Calls | As needed
Registration Team | Handles participant registrations and attendance tracking | High | Medium | Meetings, WhatsApp | Daily during event week
Faculty Advisors | Provide guidance and project feedback | Medium | High | Review Meetings | Bi-weekly, Daily during event week
StakeHolders Engagement Strategy:
Stakeholders | Engagement Strategy
Faculty Coordinator | Share weekly progress updates and obtain approvals for major decisions.
Event Coordinators | Collect event requirements and provide dashboard reports.
Volunteers | Share task assignments and track completion status.
Technical Team | Coordinate technical requirements and issue resolution.
Participants | Ensure smooth registration and event experience.
Faculty Advisors | Present project milestones and receive feedback.
Key StakeHolders:
Categories | StakeHolders
High Influence, High Interest | Faculty Coordinator, Student Project Lead
High Interest, Medium Influence | Event Coordinators, Registration Team
Medium Interest, Medium Influence | Volunteers, Technical Team
Medium Interest, Low Influence | Participants