Week 5 KPI Performance Evaluation

Project Title: Campus Cultural Fest Operations Dashboard & Process Optimization System

Objective

The purpose of this report is to evaluate the performance of the project using key performance indicators (KPIs) defined during the planning and analysis phases.

The evaluation helps determine whether project objectives were successfully achieved and identifies areas for improvement.

KPI Evaluation Summary

| KPI | Target | Actual Result | Status |
| --- | --- | --- | --- |
| Total Registrations | 600 | 650 | Achieved |
| Attendance Rate | 75% | 76.77% | Achieved |
| Total Volunteers | 20 | 20 | Achieved |
| Total Tasks Assigned | 50 | 50 | Achieved |
| Total Incidents Tracked | 40 | 40 | Achieved |
| Average Resolution Time | Less than 45 min | 34.3 min | Achieved |

KPI Analysis

Registration Performance

Target: 600 Registrations

Actual: 650 Registrations

Result

The registration target was exceeded by 50 participants.

The cultural fest attracted strong student participation across all events.

Status: Achieved

Attendance Performance

Target: 75% Attendance Rate

Actual: 76.77% Attendance Rate

Result

Attendance performance exceeded the target.

This indicates effective participant engagement and event communication.

Status: Achieved

Volunteer Resource Performance

Target: 20 Volunteers Available

Actual: 20 Volunteers Available

Result

Volunteer resources met the planned requirement.

Volunteer support was sufficient to manage registrations, event coordination, and operational activities.

Status: Achieved

Task Management Performance

Target: 50 Tasks Assigned

Actual: 50 Tasks Assigned

Result

All planned operational tasks were successfully assigned to volunteers.

Task allocation remained balanced across the volunteer team.

Status: Achieved

Incident Management Performance

Target: Track and manage all operational incidents

Actual: 40 Incidents Tracked

Result

All operational incidents were recorded and monitored through the incident management process.

This improved visibility into operational issues during the event.

Status: Achieved

Resolution Time Performance

Target: Less than 45 Minutes

Actual: 34.3 Minutes

Result

Average incident resolution time remained below the target threshold.

Operational issues were resolved within an acceptable timeframe.

Status: Achieved

Overall Project Performance

| Evaluation Area | Result |
| --- | --- |
| Registration Management | Successful |
| Attendance Management | Successful |
| Volunteer Management | Successful |
| Incident Management | Successful |
| Dashboard Development | Successful |
| Reporting & Analytics | Successful |

Key Achievements

The following achievements were observed during the project:

- Registration target exceeded by 8.3%.

- Attendance target successfully achieved.

- Volunteer resources are effectively utilized.

- Incident response times remained within target limits.

- Operational data successfully transformed into dashboard insights.

- A centralized reporting dashboard was developed and tested.

Areas for Improvement

Although project objectives were achieved, the following improvements could be considered for future events:

- Increase attendance through automated reminder communications.

- Improve volunteer scheduling during peak event periods.

- Introduce incident categorization for deeper analysis.

- Expand dashboard filtering capabilities.

Conclusion

The KPI evaluation indicates that the Campus Cultural Fest Operations Dashboard & Process Optimization System successfully achieved its objectives.

All key performance indicators met or exceeded their targets. The dashboard provided effective visibility into registrations, attendance, volunteer utilization, and incident management, supporting operational monitoring and decision-making throughout the project.