## Schedule Tracking
Task ID | Project Phase | Planned Week | Actual Week | Status | Remarks
T01 | Project Charter | Week 1 | Week 1 | Completed | Completed as planned
T02 | Stakeholder Register | Week 1 | Week 1 | Completed | Completed as planned
T03 | Process Flow Diagram | Week 1 | Week 1 | Completed | Approved after revision
T04 | Risk Register | Week 1 | Week 1 | Completed | Completed as planned
T05 | Database Schema Design | Week 1 | Week 1 | Completed | Completed as planned
T06 | ER Diagram | Week 2 | Week 2 | Completed | Completed as planned
T07 | SQL Table Creation | Week 2 | Week 2 | Completed | SQLite database created
T08 | Sample Data Generation | Week 2 | Week 2 | Completed | Python script used
T09 | Data Import & Validation | Week 2 | Week 2 | Completed | Validation successful
T10 | KPI Definition | Week 3 | Week 3 | Completed | KPIs documented
T11 | Registration Analysis | Week 3 | Week 3 | Completed | Analysis completed
T12 | Attendance Analysis | Week 3 | Week 3 | Completed | Analysis completed
T13 | Volunteer Analysis | Week 3 | Week 3 | Completed | Analysis completed
T14 | Incident Analysis | Week 3 | Week 3 | Completed | Analysis completed
T15 | KPI Dataset Preparation | Week 3 | Week 3 | Completed | Dataset created
T16 | Dashboard Requirements | Week 4 | Week 4 | Completed | Requirements documented
T17 | KPI Mapping | Week 4 | Week 4 | Completed | Completed as planned
T18 | Dashboard Development | Week 4 | Week 4 | Completed | Looker Studio dashboard built
T19 | Dashboard Testing | Week 4 | Week 4 | Completed | All tests passed
T20 | Executive Summary Report | Week 4 | Week 4 | Completed | Report prepared
T21 | Schedule Tracking | Week 5 | Week 5 | Completed | Current activity
T22 | KPI Performance Evaluation | Week 5 | Pending | Not Started | Planned
T23 | Risk Monitoring Report | Week 5 | Pending | Not Started | Planned
T24 | Lessons Learned Register | Week 5 | Pending | Not Started | Planned
T25 | Project Closure Report | Week 5 | Pending | Not Started | Planned
T26 | Final Presentation | Week 5 | Pending | Not Started | Planned
T27 | Week 5 Status Report | Week 5 | Pending | Not Started | Planned

## Project Progress Summary
Metric | Value
Total Tasks | 27
Completed Tasks | 21
In Progress Tasks | 0
Not Started Tasks | 6
Completion Percentage | 77.8%

## Status Chart
Status | Count
Completed | 21
Not Started | 6

## Conclusion
Conclusion
Project activities completed up to Week 4 were delivered according to the planned schedule. Dashboard development, testing, and reporting activities were successfully completed. Week 5 activities are focused on project evaluation and closure.