Week 5 Risk Monitoring Report

Project Title: Campus Cultural Fest Operations Dashboard & Process Optimization System

Objective

The purpose of this report is to review and monitor project risks identified during the planning phase and evaluate the effectiveness of mitigation actions taken throughout the project.

Risk monitoring helps ensure that potential issues are identified early and managed appropriately to minimize their impact on project objectives.

Risk Monitoring Approach

The following activities were performed during project execution:

- Regular review of identified risks.

- Monitoring project progress against planned activities.

- Tracking data quality and dashboard development issues.

- Implementing mitigation actions where required.

- Updating risk status throughout the project lifecycle.

Risk Status Summary

| Risk ID | Risk Description | Impact | Mitigation Strategy | Current Status |
| --- | --- | --- | --- | --- |
| R01 | Volunteer Shortage | High | Maintain backup volunteer list | Closed |
| R02 | Low Participant Attendance | High | Promote events through student groups and social media | Closed |
| R03 | Data Quality Issues | Medium | Validate generated datasets before analysis | Closed |
| R04 | Dashboard Development Delays | Medium | Complete dashboard tasks according to schedule | Closed |
| R05 | Technical Issues During Development | Medium | Perform testing and troubleshooting | Closed |
| R06 | Missing Relationships Between Tables | Medium | Validate foreign key relationships | Closed |

Detailed Risk Review

Risk R01 – Volunteer Shortage

Impact: High

Mitigation Planned: Maintain a backup pool of volunteers and distribute responsibilities evenly.

Outcome:

Twenty volunteers were successfully assigned to support event operations.

No volunteer shortages occurred during the project.

Final Status: Closed

Risk R02 – Low Participant Attendance

Impact: High

Mitigation Planned: Promote events through campus communication channels and student communities.

Outcome:

Attendance rate reached 76.77%, exceeding the project target of 75%.

Participation levels remained satisfactory throughout the event.

Final Status: Closed

Risk R03 – Data Quality Issues

Impact: Medium

Mitigation Planned: Validate generated datasets before importing into the SQLite database.

Outcome:

Record counts, field values, and relationships were validated successfully.

No major data quality issues were identified.

Final Status: Closed

Risk R04 – Dashboard Development Delays

Impact: Medium

Mitigation Planned: Follow the planned dashboard development schedule and complete tasks on time.

Outcome:

Dashboard development was completed during Week 4 according to the project plan.

Final Status: Closed

Risk R05 – Technical Issues During Development

Impact: Medium

Mitigation Planned: Perform regular testing and resolve issues during development.

Outcome:

Minor configuration issues were encountered while setting up SQLite and Looker Studio, but these were resolved without affecting project progress.

Final Status: Closed

Risk R06 – Missing Relationships Between Tables

Impact: Medium

Mitigation Planned: Validate database relationships during Week 2.

Outcome:

Relationships between registrations, attendance records, volunteers, and tasks were successfully validated.

No relationship issues remained before dashboard development.

Final Status: Closed

Risk Performance Summary

| Metric | Value |
| --- | --- |
| Total Risks Identified | 6 |
| Risks Closed | 6 |
| Risks Remaining Open | 0 |
| Risks Escalated | 0 |
| Risks Causing Project Delays | 0 |

Risk Management Effectiveness

The risk management process was effective in identifying and addressing potential project issues before they impacted project objectives.

Key strengths included:

- Early identification of project risks.

- Continuous monitoring throughout project execution.

- Timely implementation of mitigation actions.

- Regular validation of project deliverables.

As a result, no major risks affected project schedule, dashboard development, or reporting activities.

Lessons Learned from Risk Management

The following lessons were identified:

- Early risk identification improves project preparedness.

- Data validation significantly reduces reporting errors.

- Regular progress monitoring helps prevent schedule delays.

- Testing activities are important for ensuring dashboard accuracy and reliability.

Conclusion

The Campus Cultural Fest Operations Dashboard & Process Optimization System successfully managed all identified project risks. Mitigation actions were effective, and no major risks impacted project delivery. All identified risks were monitored, controlled, and closed by the end of the project.